YAT  COLLEGE

YAT College  ·  175 Cremorne St, Cremorne VIC 3121

# Business Case

YAT LMS Cloud Migration

Assessor exemplar — internal marking reference (not for distribution to students)

| Prepared for | YAT Board, via Sam Walker (YAT ICT Manager) |
| --- | --- |
| Prepared by | MTS Consultant, MP Tech Solutions (MTS) |
| Reviewed by | Pat Lin, MTS Senior Consultant |
| Engagement | YAT LMS Cloud Migration — S1-CL1 |
| Document version | v1.0 |
| Analysis period | 5 years |
| Currency | AUD, exclusive of GST |
| Classification | Commercial-in-confidence |

# Contents

Contents	2

1. Executive Summary	4

2. Engagement Context	4

3. Strategic Alignment Analysis	4

4. Current State of YAT's ICT	5

5. Gap Analysis	5

6. Options Considered and Evaluation	6

6.1 Workload definition	6

6.2 Options considered	6

6.3 Evaluation method	6

6.4 Initial impact and difficulty assessment	6

7. Cost-Benefit Analysis	6

7.1 Assumptions	7

7.2 Option A — In-house renewal (5-year summary)	7

7.3 Option B — Cloud migration to AWS (5-year summary)	7

7.4 Avoided-downtime benefit (Option B)	7

7.5 Comparison summary	7

7.6 Sensitivity analysis	8

8. Risk and Impact Assessment	8

8.1 Intangibles comparison	8

8.2 Risk register (recommended option — cloud)	8

9. Recommendation	9

10. Action Plan	9

10.1 Prioritised changes	9

10.2 Implementation schedule	9

10.3 Standards, targets, and success metrics	9

10.4 Implementation methods	10

10.5 Alignment with the change management procedure	10

11. Next Steps and Decision Requested	10

Sign-off	10

Appendix 1 — Cost-Benefit Analysis: Detailed Line Items	11

A1.1 Option A — In-house renewal	11

A1.2 Option B — Cloud migration to AWS	11

Appendix 2 — Knowledge Evidence	12

A2.1 Selection-style questions	12

A2.2 Demonstration-style questions	13

# 1. Executive Summary

Evidences: contributes to [ICTICT517 PC 1.4]

YAT's Learning Management System (DOODLE) runs on a single, end-of-supportable-life on-premises server delivering ~99.2% availability — short of the 99.9% target the ICT Strategic Plan sets for critical systems, and unable to meet the recovery and capacity expectations of a growing RTO. This Business Case evaluates two options over a five-year horizon: Option A — renew the on-premises server; Option B — migrate the LMS to Amazon Web Services (AWS) in the Sydney region (ap-southeast-2), preserving the existing Windows Server 2016 / DOODLE / MySQL stack.

The five-year direct cost of the two options is comparable (~$447,300 on-premises vs ~$441,400 cloud). The decision therefore turns on the non-cost factors: only Option B credibly achieves 99.9% availability and the RTO ≤ 4h / RPO ≤ 1h recovery objectives, and only Option B provides the elastic capacity for 15% annual student growth and the ~3× assessment-window peaks. Quantifying the avoided downtime adds ~$69,000 of benefit to the cloud option over five years, giving it the stronger net position (~$372,400 vs ~$447,300).

The principal risks of the cloud option — staff upskilling, cost control, and a safe cutover — are manageable through continued MTS support, AWS cost guardrails, and phased migration outside assessment windows. We recommend Option B and ask the board to approve the migration, the phased action plan in §10, and the Year-1 budget envelope.

# 2. Engagement Context

Evidences: [ICTICT517 AC 4]

This Business Case is prepared by MP Tech Solutions (MTS) for the YAT Board, via the YAT ICT Manager (Sam Walker), under the MTS–YAT Master Services Agreement, and reviewed by the MTS Senior Consultant (Pat Lin) before submission. MTS has been engaged to analyse YAT's LMS operating-model options and recommend a way forward. It asks the board to decide whether to renew the LMS on-premises or migrate it to AWS, and to approve the associated action plan and Year-1 budget.

# 3. Strategic Alignment Analysis

Evidences: [ICTICT517 PC 1.1] · [ICTICT517 PE 1]

YAT's ICT Strategic Plan sets goals to ensure reliable ICT services, respond quickly to change, reduce dependency on in-house server infrastructure, and adopt sustainable practices. Three objectives are material to this engagement: investigate transitioning critical on-premises application services to the cloud (by mid-2027); deploy the LMS in the cloud (by end-2027); and achieve 99.9% availability for critical systems (by end-2027). The plan names the LMS as the first system to transition, making this engagement the lead initiative of the strategy. These ICT objectives in turn serve YAT's business objectives — location-independent learning, national expansion, and 15% annual student growth — for which the plan identifies cloud-hosted infrastructure as the principal ICT enabler.

Against the industry environment, the direction is well aligned: Australian RTOs and the wider education sector are moving steadily to cloud and managed services, shifting from capital refresh cycles (CAPEX) to consumption-based operating costs (OPEX), and treating resilience and elastic capacity as baseline expectations rather than premium features. Data-residency obligations under the Privacy Act 1988 (APP 8) and the Standards for RTOs 2015 are equally part of that environment, and are met by deploying in an Australian region.

Where YAT's plan is more ambitious than its current posture is the 99.9% availability target — a meaningful step up from the measured 99.2% and one a single on-premises server cannot credibly deliver. That ambition is appropriate, not excessive: it reflects the LMS's mission-critical role. The implication is clear — the LMS migration is the proving ground for the broader strategy, and delivering it well sets the pattern for moving YAT's other suitable on-site systems to the cloud.

# 4. Current State of YAT's ICT

Evidences: [ICTICT517 PC 1.2] · [ICTICT517 PE 2]

YAT's network is resilient at the infrastructure layer (no single point of failure, dual-NIC servers, two AD-controlled security zones), but the LMS itself is not. DOODLE runs on a single Windows Server 2016 host with a MySQL database and ~178 GB of data (of ~250 GB allocated), and the server is at end of supportable life. Measured availability is 99.2%; recovery rests on nightly tape backups, giving an RPO of ~24 hours and an RTO of ~7–11 hours — both well short of the migration targets. The LMS integrates with Active Directory (authentication), Office 365 (notifications), the Accounting system (fee-status), and ASQA/DET reporting. YAT ICT staff are highly capable on-premises but have limited cloud experience; MTS provides application support under a standing contract. The material limitations for this decision are the single point of failure, the end-of-life hardware, recovery objectives far from target, and fixed capacity that cannot absorb the ~3× assessment-window peaks or 15% annual growth without over-provisioning.

# 5. Gap Analysis

Evidences: [ICTICT517 PC 1.3] · [ICTICT517 PE 3]

| Strategic objective | Current state | Desired future state | Gap | Improvement opportunity | Proposed change |
| --- | --- | --- | --- | --- | --- |
| 99.9% availability for critical systems | 99.2% on a single server | 99.9% (Multi-AZ resilient) | ~0.7 pp (~61 hr/yr); single server cannot deliver | Highly available architecture | Migrate to AWS across two Availability Zones |
| Reduce dependency on in-house infrastructure | Owns/runs end-of-life server + room | No in-house server to own or run | Full reliance on self-run hardware | Managed cloud operating model | Migrate LMS to AWS (managed services) |
| Recover quickly (RTO ≤ 4h / RPO ≤ 1h) | RTO ~7–11h, RPO ~24h (nightly tape) | RTO ≤ 4h, RPO ≤ 1h | Hours-to-a-day short on both | Automated backups + failover | RDS Multi-AZ + AWS Backup |
| Scale for growth and assessment peaks | Fixed server, no elasticity | Auto-scale to ~3× peaks; absorb 15%/yr | No elasticity; over-provision or degrade | Elastic compute | EC2 Auto Scaling; scale in off-peak |

The gaps cluster around resilience, recovery, capacity, and ownership. An on-premises refresh (Option A) addresses end-of-life hardware but leaves the single point of failure, the recovery shortfall, and the fixed capacity largely intact. A cloud operating model (Option B) addresses all four. This is the central finding the options analysis tests.

# 6. Options Considered and Evaluation

Evidences: [ICTICT517 PC 2.1] · [ICTICT517 PC 2.2] · [ICTICT517 KE 3] · [ICTCLD401 PC 1.8] · [ICTCLD502 PC 1.2]

## 6.1 Workload definition

The LMS serves ~860 users (≈800 students + 60 staff), with 200–300 typical concurrent users, 500–700 at peak (~3× for the ~10–14-day assessment window each term), and very low overnight/term-break load. Data is ~178 GB, growing ~25 GB/year. It must preserve the Windows Server 2016 / DOODLE / MySQL stack with full OS control, keep its AD, Office 365, Accounting and ASQA integrations, hold all data in Australia, and meet 99.9% availability, RTO ≤ 4h and RPO ≤ 1h.

## 6.2 Options considered

Option A — In-house renewal: replace the end-of-life server and ancillary hardware; retain the single-site on-premises operating model.

Option B — Cloud migration to AWS: redeploy the LMS onto a highly available AWS architecture (EC2 Auto Scaling across two AZs, RDS Multi-AZ for MySQL, ALB), preserving the OS and application stack.

A standalone managed-hosting option was considered but not carried forward separately: its benefits (no in-house server, managed resilience) are a subset of Option B's, while AWS adds the elasticity and recovery posture the requirements demand.

## 6.3 Evaluation method

Each option is evaluated with a five-year cost-benefit analysis (§7), a quantified avoided-downtime benefit (§7.4), an intangibles comparison (§8.1), and a risk register (§8.2). This combination is appropriate because the decision turns on both cost and non-cost factors — resilience, capacity, and strategic alignment — that a cost comparison alone would not capture.

## 6.4 Initial impact and difficulty assessment

|  | Option A — In-house | Option B — Cloud (AWS) |
| --- | --- | --- |
| Strategic impact | Refreshes hardware but leaves the 99.9% target out of reach | Directly delivers the strategy's lead initiative and availability target |
| Implementation difficulty | Low — familiar in-house refresh | Moderate — new platform; mitigated by MTS and a phased plan |
| Headline pros | Cheap upfront; uses existing skills | Meets availability/recovery/scaling targets; reduces in-house burden |
| Headline cons | Single point of failure persists; fixed capacity | Higher Year-1 outlay; cloud upskilling; vendor dependency |

# 7. Cost-Benefit Analysis

Evidences: [ICTICT517 PC 2.1] · [ICTICT517 KE 3] · [ICTICT517 FS Numeracy] · [ICTCLD401 KE 4] · [ICTCLD502 KE 3] · [ICTCLD401 KE 1]

A five-year CBA comparing the two options (AUD ex GST). Detailed line items are in Appendix 1; AWS figures are indicative, sized per §6.1 and backed by a Pricing Calculator export. A 3% annual inflation factor is applied to recurring costs from Year 2.

## 7.1 Assumptions

| Assumption | Value | Used as-is? |
| --- | --- | --- |
| LMS user population | 800 students + 60 staff | Yes |
| Annual student growth | +15% per year | Yes |
| Current / target availability | 99.2% / 99.9% | Yes |
| ICT FTE fully-loaded cost | $115,000 / year (≈$63.19/hr) | Yes |
| Cost of downtime (teaching hours) | $750 / hour | Yes |
| Inflation applied to recurring | 3% per year from Year 2 | Adjusted — see note |
| AWS region | ap-southeast-2 (Sydney) | Yes (data residency) |

## 7.2 Option A — In-house renewal (5-year summary)

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5-year |
| --- | --- | --- | --- | --- | --- | --- |
| One-off capital | $51,000 | — | — | — | — | $51,000 |
| Recurring | $74,650 | $76,890 | $79,196 | $81,572 | $84,019 | $396,327 |
| Annual total | $125,650 | $76,890 | $79,196 | $81,572 | $84,019 | $447,327 |

## 7.3 Option B — Cloud migration to AWS (5-year summary)

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5-year |
| --- | --- | --- | --- | --- | --- | --- |
| One-off project | $108,500 | — | — | — | — | $108,500 |
| AWS direct | $27,250 | $28,068 | $28,910 | $29,777 | $30,670 | $144,675 |
| Staff + external | (in project) | $45,000 | $46,350 | $47,741 | $49,173 | $188,264 |
| Annual total | $135,750 | $73,068 | $75,260 | $77,518 | $79,843 | $441,439 |

## 7.4 Avoided-downtime benefit (Option B)

|  | Calculation | Value |
| --- | --- | --- |
| Avoided unavailability / year | (0.008 − 0.001) × 8,760 hr | 61.3 hr |
| Proportion during teaching hours | assumption | 30% |
| Avoided downtime cost / year | 61.3 × 30% × $750 | $13,800 |
| 5-year avoided-downtime benefit | × 5 | $69,000 |

## 7.5 Comparison summary

|  | Option A | Option B | Delta (B − A) |
| --- | --- | --- | --- |
| One-off (Year 1) | $51,000 | $108,500 | +$57,500 |
| Recurring (5-year) | $396,327 | $332,939 | −$63,388 |
| 5-year direct cost | $447,327 | $441,439 | −$5,888 |
| Avoided-downtime benefit | — | $69,000 | −$69,000 |
| Net 5-year position | $447,327 | $372,439 | −$74,888 |

On direct cost the options are within ~1.3% over five years. Option B carries a higher Year-1 outlay but lower recurring cost, and once the avoided-downtime benefit is included it is ~$74,900 ahead on net position — before the unpriced strategic and capacity benefits.

## 7.6 Sensitivity analysis

Sensitivity 1 — teaching-hours downtime proportion 30% → 50%: the avoided-downtime benefit rises from ~$69,000 to ~$115,000 over five years, widening Option B's net advantage. The recommendation is reinforced.

Sensitivity 2 — MTS migration labour $60,000 → $80,000: Option B's five-year direct cost rises to ~$461,400, slightly above Option A; but after the avoided-downtime benefit its net position (~$392,400) remains well below Option A's $447,327. The recommendation holds.

# 8. Risk and Impact Assessment

Evidences: [ICTICT517 PC 2.1] · [ICTICT517 PC 2.2] · [ICTICT517 PE 5]

## 8.1 Intangibles comparison

| Factor | Option A — In-house | Option B — Cloud (AWS) |
| --- | --- | --- |
| 99.9% availability target | Not credibly achievable on a single server | Achievable via Multi-AZ deployment |
| Recovery (RTO ≤ 4h / RPO ≤ 1h) | Improves but stays single-site | Met via RDS Multi-AZ + automated backups |
| Capacity for 15% growth | Needs over-provisioning / re-refresh | Scales on demand |
| Assessment-week peaks (~3×) | Must size for peak year-round | Auto-scales for peaks |
| Staff capability impact | Uses existing skills | Requires upskilling (MTS-supported) |
| Vendor lock-in | None new | AWS dependency; standard stack aids portability |
| Sustainability | Runs own server + room | Shared, efficient cloud infrastructure |
| DR (whole-campus loss) | Slow tape restore offsite | Cross-Region backup copy |

## 8.2 Risk register (recommended option — cloud)

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Cloud cost overrun / bill shock | Medium | Medium | Budgets + CloudWatch alarms; tagging; Savings Plans for baseline |
| Staff cloud-skills gap | High | Medium | MTS support contract; AWS training; documented runbooks |
| Data loss/corruption during migration | Low | High | Parallel running; verified backups; tested rollback |
| Cutover disrupts teaching | Medium | High | Schedule outside assessment windows; maintenance window; comms plan |
| Vendor dependency | Low | Medium | Standard Windows/MySQL stack; infrastructure-as-code; documented exit plan |

# 9. Recommendation

Evidences: [ICTICT517 PC 2.3] · [ICTICT517 PE 4] · contributes to [ICTICT517 PC 3.1]

Recommended option: Option B — Cloud migration to AWS. Over five years the two options are effectively cost-neutral on direct spend, but only the cloud option meets the 99.9% availability target and the RTO ≤ 4h / RPO ≤ 1h recovery objectives, scales for 15% growth and the assessment-window peaks, and materially improves disaster recovery. The avoided-downtime benefit puts it ahead on net cost as well. The main risks — upskilling, cost control, and a safe cutover — are manageable and addressed in §8.2 and §10. This recommendation drives the prioritisation and action plan below.

# 10. Action Plan

Evidences: [ICTICT517 PC 3.1] · [ICTICT517 PC 3.2] · [ICTICT517 PE 6] · [ICTICT517 KE 1]

## 10.1 Prioritised changes

| # | Change | Priority rationale |
| --- | --- | --- |
| 1 | Stand up the AWS foundation (network, IAM, guardrails) | Everything else depends on a secure, governed landing zone |
| 2 | Build the highly available LMS infrastructure (EC2 ASG Multi-AZ, RDS Multi-AZ, ALB) | Delivers the availability/recovery/scaling targets before any data moves |
| 3 | Deploy DOODLE and migrate the MySQL data; run in parallel | Validate the new platform against the live system before commitment |
| 4 | Cut over and decommission the on-premises server | Final, highest-risk step; only after parallel-run acceptance |

## 10.2 Implementation schedule

| Phase | Activities | Start | Duration | Dependencies | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | AWS foundation + design review | Wk 1 | 2 wks | — | MTS |
| 2 | HA infrastructure build | Wk 3 | 3 wks | Phase 1 | MTS |
| 3 | App deploy + data migration + parallel run | Wk 6 | 3 wks | Phase 2 | MTS + YAT ICT |
| 4 | Cutover + decommission | Wk 9 | 1 wk | Phase 3 acceptance | YAT ICT + MTS |

Scheduling avoids month-end and the two-week assessment windows; the cutover runs in an approved maintenance window with a tested rollback.

## 10.3 Standards, targets, and success metrics

| Aspect | Standard / target | How measured |
| --- | --- | --- |
| Availability | 99.9% | CloudWatch uptime over rolling 12 months |
| Recovery | RPO ≤ 1h / RTO ≤ 4h | DR test results; backup frequency |
| Data residency | Australia (ap-southeast-2) | AWS Config region check |
| Cost envelope (Year 1) | ≈ $135,750 | Actuals vs budget in Cost Explorer |

## 10.4 Implementation methods

Each phase applies an AWS Well-Architected review at its design milestone, infrastructure-as-code (CloudFormation) for repeatable builds, and YAT's Change Management Procedure for all production changes.

## 10.5 Alignment with the change management procedure

Phases 2–4 raise change requests; the Phase 4 cutover is a high-risk change requiring Change Advisory Board endorsement and ICT-Manager approval, with the budget and option decision approved by the board via this Business Case.

# 11. Next Steps and Decision Requested

Evidences: [ICTICT517 PC 3.3]

We ask the board today to: (1) approve Option B — cloud migration to AWS — as the recommended approach; (2) approve the phased action plan in §10 as the implementation roadmap; and (3) authorise the Year-1 budget envelope (≈$135,750). The high-risk cutover change request is deferred to the appropriate phase gate, per the change management procedure.

# Sign-off

Evidences: [ICTICT517 PC 3.3]

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| Prepared by | MTS Consultant |  |  |
| Reviewed by | Pat Lin (MTS Senior Consultant) |  |  |
| Approved by | Sam Walker (YAT ICT Manager) |  |  |

# Appendix 1 — Cost-Benefit Analysis: Detailed Line Items

Evidences: [ICTICT517 FS Numeracy] · [ICTICT517 KE 3] · [ICTCLD401 KE 4] · [ICTCLD502 KE 3]

## A1.1 Option A — In-house renewal

One-off capital (Year 1):

| Item | Cost |
| --- | --- |
| Replacement LMS server | $25,000 |
| Backup tape library refresh + drive | $8,000 |
| UPS upgrade | $3,000 |
| One-off migration labour (in-house) | $15,000 |
| Total Year-1 capital | $51,000 |

Recurring operational (per year):

| Category | Item | Annual cost |
| --- | --- | --- |
| Software licensing | Windows Server Standard | $1,500 |
|  | Antivirus / EDR | $300 |
|  | Monitoring / management tooling | $2,000 |
| Power & facilities | Electricity + cooling | $1,200 |
|  | Server-room rent allocation | $5,000 |
|  | UPS battery (amortised) | $500 |
| Backup | Tape media | $1,500 |
|  | Offsite tape storage | $2,400 |
|  | Backup software maintenance | $1,500 |
| Staff (YAT ICT) | LMS admin (0.20 FTE) | $23,000 |
|  | Incident response (0.05 FTE) | $5,750 |
| External support | MTS application support | $30,000 |
| Total recurring per year |  | $74,650 |

## A1.2 Option B — Cloud migration to AWS

One-off project costs (Year 1):

| Item | Cost |
| --- | --- |
| MTS migration labour (design + build) | $60,000 |
| YAT ICT staff time during migration (oversight, deploy, data, cutover, change mgmt) | $38,000 |
| Parallel running of on-prem + cloud during cutover | $7,000 |
| Decommissioning + secure data destruction | $3,500 |
| Total Year-1 project | $108,500 |

AWS direct recurring (per year, indicative — ap-southeast-2):

| Category | Service / item | Annual cost |
| --- | --- | --- |
| Compute | EC2 baseline (2× Windows m6i.xlarge, Multi-AZ, Savings Plan) | $8,400 |
|  | EC2 auto-scaling (assessment-window peaks) | $1,500 |
| Database | RDS for MySQL — Multi-AZ (1-yr RI) | $6,800 |
|  | RDS storage + automated backups | $1,400 |
| Network | Application Load Balancer | $850 |
|  | NAT Gateway (×2, AZ-redundant) | $1,300 |
|  | Data transfer out | $900 |
| Storage | EBS volumes (web tier) | $700 |
|  | S3 (attachments + snapshots) | $600 |
|  | AWS Backup (incl. cross-Region copy) | $1,200 |
| Monitoring | CloudWatch (metrics + logs + alarms) | $700 |
| Support | AWS Business Support (≤1h sev-1) | $2,900 |
| AWS direct per year |  | $27,250 |

Staff + ongoing external support (per year, Years 2–5):

| Item | Annual cost |
| --- | --- |
| YAT ICT staff time (admin/monitoring, reduced — 0.10 FTE) | $11,500 |
| YAT ICT staff time (incident response — 0.03 FTE) | $3,450 |
| MTS ongoing support (application + cloud infrastructure) | $30,000 |
| Staff + external per year | $44,950 |

# Appendix 2 — Knowledge Evidence

Underlying knowledge as applied to the work presented above.

## A2.1 Selection-style questions

| Question | Response |
| --- | --- |
| Service model of each AWS component (IaaS/PaaS/SaaS) and why [ICTCLD401 KE 3] | EC2 = IaaS (full OS control is required to host DOODLE on Windows Server 2016). RDS, ALB, S3, AWS Backup, CloudWatch = PaaS-style managed services (chosen to offload operations from a thin in-house team). Office 365 (email) = SaaS. |
| Deployment model and why [ICTCLD401 KE 11] | Public cloud. YAT has no regulatory reason to run private infrastructure, already uses SaaS (O365), and gains managed resilience and elasticity it cannot achieve on-prem; data residency is met by an Australian region. |
| Industry standards that informed the approach (≥3) [ICTCLD401 KE 1] · [ICTCLD502 KE 1] | NIST SP 800-145 (service-model definitions); AWS Well-Architected (design + the Reliability pillar behind the HA design); ISO/IEC 27017 and the ACSC Essential Eight (cloud security controls); the Privacy Act / APP 8 (data-residency region choice). |
| Industry-standard products in the solution and their role [ICTCLD401 KE 2] · [ICTCLD502 KE 2] | EC2 (compute hosting DOODLE), RDS for MySQL (managed database), Application Load Balancer (traffic distribution across AZs), S3 (object storage for attachments/snapshots), CloudWatch (monitoring/alarms). |
| Cloud cost model(s) applied and why [ICTCLD401 KE 4] · [ICTCLD502 KE 3] | Reserved Instances / Savings Plans for the always-on baseline (compute, RDS); on-demand auto-scaling for the assessment-window peaks; pay-as-you-go for storage and data transfer. The model follows the workload's demand shape, so cost tracks usage. |

## A2.2 Demonstration-style questions

| Question | Response |
| --- | --- |
| How does §10 demonstrate the key sections of an action plan? [ICTICT517 KE 1] | §10.1 prioritised changes; §10.2 schedule with durations/dependencies/owners; §10.3 standards, targets and success metrics; §10.4 methods; §10.5 change-management alignment. |
| Evaluation and planning methods applied [ICTICT517 KE 2] | Five-year CBA (§7), avoided-downtime quantification (§7.4), sensitivity analysis (§7.6), intangibles comparison (§8.1), and a risk register (§8.2). |
| How competing products were evaluated [ICTICT517 KE 3] | Option A vs Option B compared on cost (§7), strategic impact and difficulty (§6.4), intangibles (§8.1) and risk (§8.2). |
| Emerging trends that informed the recommendation [ICTICT517 KE 4] | Sector shift to managed cloud and OPEX-over-CAPEX, and elastic capacity as a baseline expectation — material to choosing a cloud operating model over a hardware refresh. |